Evaluation Plan

Generational Resources & Opportunities for Well-Being (G.R.O.W)

Research Questions:

Phase 1: Phase 1 includes short-term research questions focused on program implementation, in order to adjust and improve the program moving forward. These questions will guide the evaluation through the first year of implementation, continuing throughout the length of the program.

- Did the program meet key performance measures and outputs (# of accounts enrolled, incentives distributed, $ investment, and engagement)?

- Who is the program benefitting? (Demographic breakdown by race/ethnicity, age, gender, family structure, household income, parents’ education)

  - How did key performance measures differ across participant demographics?

- To what extent were incentives utilized by participants (i.e. teachers and scholars)?

- What are some key successes and challenges of the program and its design, according to participants, educators, and ambassadors?

- What is the projected SROI for G.R.O.W to the Jacksonville community?

Phase 2: Phase 2 includes intermediate research questions focused on initial program outcomes & impact, allowing for a projection of program success. These questions will guide the evaluation through years 2 & 3.

- Did the program improve educational outcomes for participants (as compared to comparison schools)?

  - Did program participants show improvements in attendance?

  - Did program participants show improvement in behavior?

  - Did program participants show improvement in reading milestones?

  - Did the program increase aspirations to attend post-secondary education (PSE) among participants?

  - Do participants perceive the program as being beneficial to asset & wealth building for their future endeavors?

- Did the program improve economic outcomes for participants?

  - Did the program increase financial literacy among participants?

  - Did the program increase financial resources available for participants' future education or career endeavors?

- What is the evaluative social return on investment (SROI) of the program to the Jacksonville community (updated on a yearly basis), and the projected future SROI of the program (updated on a yearly basis)

  - How does the projected SROI for G.R.O.W compare to other educational and wealth building programs? Analysis dependent on the availability of data on similar programs.

Future Research Questions: The following research questions are questions that could possibly be answered in the future with a longer timeline, but that are unable to be answered at the onset of the program. Therefore, these questions will not be addressed throughout the rest of the evaluation plan.

Phase 3: long-term research questions focus on large scale program outcomes & impact, allowing for the analysis of long term program success. These questions are for long term evaluation, to be conducted 10-15 years out (For example, for a 5 y.o. kindergarten participant enrolled in 2024, the earliest these evaluation questions could be addressed is in 2035 when that participant is 16 y.o.).

- To what extent did the G.R.O.W impact long term economic outcomes of participants compared to non-participants?

  - How many participating scholars have:

    - A job at 16 years old?

    - A debit card and/or checking account at 16 years old?

    - Graduated high school?

    - Enrolled in post-secondary education ?

- To what extent did G.R.O.W impact school-level outcomes for participating schools (compared to other similar schools)?

  - To what extent did student enrollment increase in participating schools?

  - To what extent did teacher recruitment and retention improve in participating schools?

- To what extent have community-level economic factors related to social vulnerability in  Jacksonville? (i.e. poverty, unemployment, income, and high school graduation rates) changed since the introduction of G.R.O.W?.

- To what extent has this program proven to be more effective than other educational and wealth building programs?

Logic Model:

| Inputs | Activities | Outputs | Short term Outcomes | Intermediate Outcomes | Long Term Outcomes |
| --- | --- | --- | --- | --- | --- |
| Funding from Tempus Realty Partners Partnership with Jacksonville North Pulaski School District (JNPSD) Year 1 participation of Jacksonville Murrell Taylor Elementary School (JMTE) Arkansas Brighter Futures 529 contracts & accounts All scholars of Jacksonville Murrell Taylor Elementary School Teachers at Jacksonville Murrell Taylor Elementary School Jacksonville Murrell Taylor Elementary School School Board support Partnership with Economics Arkansas (EA) | Tempus: Distribute $10,000 grant to JNPSD Launch opt in/out enrollment for 529 accounts among 431 JMTE scholars $600 Seed deposit into each scholar enrollees account Deposit $600 annually for enrollees from 1st-5th grade Offer up to $300 annually per scholar participant through incentives Provide 529 accounts for participating teachers Offer monetary incentives to participating teachers to be distributed into 529 accounts JNPSD: Recruitment of one G.R.O.W ambassador s from Jacksonville Murrell Taylor Elementary School Incorporate G.R.O.W opt in/opt out into annual scholar registration process Distribute $5,000 stipend (from Tempus) for G.R.O.W ambassador Provide $5,000 (from Tempus) for community engagement activities Provide convening of and access to K-5th teachers monthly to allow for EA to provide PD on G.R.O.W curriculum Provide feedback for G.R.O.W evaluation (Years 2-3) expand the program to additional schools G.R.O.W ambassador: dedicate 12-15 hours per month to promote G.R.O.W. among scholars, teachers, and parents at JMTE Facilitate enrollment of scholars and teachers into Arkansas Brighter Futures 529 Leads ongoing data collection including data tracking and reports for financial incentives/incentives awards Works with EA to facilitate, distribute, and train teachers with financial education curriculum Provide feedback for G.R.O.W evaluation Economics Arkansas: Create K-5th financial educational curriculum Provide professional development for teachers to deliver financial education curriculum Arkansas Brighter Futures 529: Establish and maintain savings accounts for participants Provide 529 education and promotion through G.R.O.W events Share account data for G.R.O.W evaluation CSIC Evaluation Team: Conduct evaluation over three years of program implementation Provide recommendations for program improvement on a yearly basis Provide forecasted & evaluative SROIs of the program | # of enrollments per year # of G.R.O.W ambassadors participating per year (i.e. teachers) # of deposits (and $ amounts) made by families into the accounts # of deposits (and $ amounts) made by Tempus # of (and $ dollar amounts) of student incentives rewarded, per type of incentive # of (and $ amount) of teacher incentives rewarded, per type of incentive Average % investment growth of accounts | Increased # of eligible families with child savings accounts Increased exposure to financial literacy among scholars & teachers Increased access to wealth building among teachers | Demonstrated growth of child savings accounts through direct deposits and incentives Increased financial resources available for participants Increase financial literacy among participants Improved attendance, reading, and behavioral outcomes for scholar participants Improved attendance, program participation, financial literacy, data collection, and engagement among teacher participants Increase aspirations/ expectations for child to attend post-secondary education and/or build wealth for children Increased teacher retention Increased student enrollment in Jacksonville School District | Increased # of Jacksonville participants who go on to attend post-secondary education Increased lifetime earnings among Jacksonville families |

Data Collection Plan:

Secondary Data & Data Agreements: Data sharing between the following entities and the CSIC evaluation team will be needed to complete the proposed evaluation:

- Jacksonville North Pulaski School District: Community Ambassadors will be tracking participation, incentives distribution, school attendance, academic data, etc. This data will need to be shared with the evaluation team regularly.

  - Data from comparison schools (i.e. schools NOT participating) in Jacksonville county will also be needed

- Arkansas Brighter Futures 529: 529 account reports will need to be shared regularly including account enrollment and investment data.

- Economics Arkansas: EA will need to regularly share the curriculum, professional development data (i.e. participation), and data on the incentive through EA.

- Tempus Realty Partners: Reports on investment data will need to be shared on a yearly basis

Data Collection Activities:

Phase 1:

- Enrollment Survey: A survey will be sent out to parents/caregivers of the enrolled scholars as soon after enrollment as possible. This survey will cover demographics of the child enrolled as well as general information about the household (ex: income, # in household), likelihood of childhood to attend Post secondary Education (PSE) and current savings for the child's PSE.

- Analysis of Quantitative Data: this includes analysis of 529 accounts, cost data, incentive data etc. (i.e. all data listed under Data Agreements).

- Annual Follow-up surveys of participants: 1 year following enrollment, participants (i.e. parents/caregiver of enrolled child AND teachers) will be sent a survey via email. This survey will be conducted annually and incentivized with a Walmart gift card. The survey will serve as a post test to the initial enrollment survey, and will also include questions about program satisfaction.

  - 400 survey responses will be collected per year, including both educator and parent participants. 400 surveys will be collected annually, including if the program is expanded to additional schools.

- Annual Interview with G.R.O.W ambassador: Conduct one interview with the designated G.R.O.W ambassador to discuss program challenges, success, and perceptions of program benefits. This will happen annually. In years 2 & 3 if the program has expanded to multiple schools, each G.R.O.W ambassador from each school will be interviewed.

- Annual Interviews with program partners: This will include interviews with relevant implementation stakeholders from Tempus, JNPSD, Arkansas Brighter Futures 529, & Economic Arkansas to determine their perception of program implementation challenges and successes.

- Annual Focus group with G.R.O.W educators: Participating educators will be invited to participate in one focus group annually. This focus group will include ambassadors' perceptions of program challenges and successes, as well as their general perceptions of the program. This focus group will be incentivized with a Walmart gift card.

  - In Year 1, one focus group will be conducted. If expanded to multiple schools in years 2 & 3, one focus group will be conducted per participating school.

  - (Added August 12th – Comment from Driver) Include pre-survey or intro question for educators:

    - “How many of the lessons did you do with your students?

    - How much time did you spend on this overall? (ie. per week, prep vs. instruction-time)

- Annual Focus groups with parents of enrolled children: Up to 5 focus groups (maximum of 10 participants per focus group) will be conducted with parents and caregivers of enrolled children. Focus groups participants will be asked about program challenges and successes, as well as questions about their & their child's intentions for saving and post secondary education. Focus groups will be incentivized with a Walmart gift card.

  - In Year 1 three focus groups will be conducted with up to 10 participants per focus group. If the program is expanded to additional schools (in years 2 & 3), these 3 focus groups will be spread across parents at each participating school (For example: 1 focus group per school)

- Yearly Social Return on Investment (SROI) Forecast calculation: As was done with the pre-project projection, each year a SROI forecast will be conducted for the upcoming year of program implementation (i.e. end of year 1, a forecast SROI of year 2 will be completed). The forecast SROI will take into account any program implementation changes as well as current data, in order to create a more accurate forecast of the Social Return on Investment of the program in the coming year(s).

- (Added August 12th – Comment from Driver) Attendance Research

  - Line graph with overall attendance rates from 5 year period (2021-2027) for Murrell Taylor + Comparison School

Phase 2:

- Attendance, behavioral, & academic data: Given that teachers will be tracking attendance, behavioral, and reading milestones, we hope to have access to a baseline on these indicators to see if participants showed a change or improvement. If this is not available to view on an individual student basis, it could also be helpful to view these indicators school wide to show change or improvement over time.

- Annual Comparison School Analysis: An analysis of outcomes (attendance, behavior, reading, financial literacy, etc.) will be completed between the participating school, and non participating schools in the Jacksonville School District to determine the programs impact on educational and financial outcomes.

- Annual Student Literacy Financial Pre-Post Quiz: Participating scholars will be given an annual financial literacy quiz, to be distributed by the G.R.O.W ambassador (i.e participating teacher) prior to and following each workshop. Financial literacy quiz will be adapted from the workshop content created by Economics Arkansas.

- Yearly SROI evaluative calculation: Each year an evaluative SROI calculation will be done using the data collected from the past year(s). This calculation will provide a more accurate understanding of the social return of the project thus far. It can also be used to compare to the previous years SROI projection.

Indicator Chart:

| Phase 1 |  |  |
| --- | --- | --- |
| Evaluation Question | Indicator/Measure | Data Source |
| Did the program meet key performance measures and outputs (# of accounts enrolled, incentives distributed, $ investment, and engagement)? | # of accounts initiated Total & average account balance Family contributions, $ amount, total & average Contributions from incentives ($) Account investment earnings ($ and % of total balance) Account investment growth rate | Arkansas Brighter Futures 529 account activity reports Incentive Distribution Data |
| Who is the program benefitting? (Demographic breakdown by race/ethnicity, age,gender, family structure, household income, parents’ education) - How did key performance measures differ across participant demographics? | Race/ethnicity of child Gender of child Eligible for free/reduced lunch Household income Household size/structure Language spoken at home Current savings for child’s education | Enrollment Survey Focus group with parents of enrolled scholars |
| To what extent were incentives utilized by participants (i.e. teachers and scholars)? | Number of incentives distributed by type Perceptions of incentive attainability and utility for both scholars and teachers | Incentive Distribution Data Interview with G.R.O.W ambassador Focus groups with G.R.O.W teacher participants Focus group with parents of enrolled scholars |
| What are some key successes and challenges of the program and its design, according to participants, educators, and ambassadors? | Program challenges and successes pointed out by G.R.O.W ambassador & program participants (i.e. teachers and parents of scholars) Program implementation challenges and successes identified by program partners | Focus group with G.R.O.W teacher participants Focus group with parents of enrolled scholars Interview with G.R.O.W ambassador Interviews with program partners Annual Follow-up surveys of participants (teachers & scholars) |
| What is the projected SROI for G.R.O.W to the Jacksonville community? | Identified value areas from project Estimated monetary benefit of value areas Forecasted SROI estimate per participant | Pre-project SROI estimate Literature Review Yearly SROI forecasting calculation Cost data from Tempus |
| Phase 2 |  |  |
| Evaluation Question | Indicator/Measure | Data Source |
| Did the program improve educational outcomes for participants? (as compared to comparison schools) - Did program participants show improvements in attendance? - Did program participants show improvement in behavior? - Did program participants show improvement in reading milestones? - Did the program increase aspirations to attend post-secondary education (PSE) among participants? - Do participants perceive the program as being beneficial to asset & wealth building for their future endeavors? | % of enrolled scholars with improvements in attendance, academic, or behavioral outcomes % of parents that report increased likelihood of their child will attending post-secondary education % of parents that report importance of wealth building for their child Perception of likelihood that child will attend college or tech school Perception of program utility in wealth building for participants (teachers & parents of enrolled children) | Attendance & academic data from the school Comparison School Analysis Enrollment Survey Arkansas Brighter Futures 529 account activity reports Follow-up survey with participants (teachers & scholars) Interview with G.R.O.W ambassador Focus group with G.R.O.W teacher participants Focus group with parents of enrolled scholars |
| Did the program improve economic outcomes for participants? - Did the program increase financial literacy among participants? - Did the program increase financial resources available for participants' future schooling or career endeavors? | % of enrolled scholars with improved financial literacy $$ and % increase in financial resources available for child’s education % of parents that report increased likelihood of their child will attending college or tech school Perception that participants are wealth building for their future (both teachers and scholars) | Student Financial Literacy Quiz Enrollment Survey Arkansas Brighter Futures 529 account activity reports Follow-up survey with participants (teachers & scholars) Focus group with parents of enrolled scholars Focus group with G.R.O.W teacher participants |
| What is the projected social return on investment (SROI) of the program to the Jacksonville community? - How does the projected SROI for G.R.O.W compare to other educational and wealth building programs? | Identified value areas from project Annual amount invested per child & as a program whole Forecasted SROI estimate per participant | Pre-project SROI estimate Literature Review Yearly SROI evaluative calculation Cost data from Tempus |

Timeline:

Phase 1- Year 1 (Spring/ Fall 2025 - Fall 2026)

- Spring 2025 - Spring 2026: Enrollment surveys distributed

- Throughout year 1: Quarterly Arkansas Brighter Futures 529 reports sent to evaluators

- Fall 2025: Distribute Student Literacy Financial Pre Quiz

- Spring 2026: Distribute Student Literacy Financial Post Quiz

- Spring 2026: Interview with G.R.O.W ambassador

- Spring 2026: Interview with program partners

- Spring 2026: Focus group with parents of enrolled scholars

- Spring 2026: Focus group with G.R.O.W educators

- Spring 2026: Tempus cost data due to evaluators

- Summer 2026: Yearly SROI Forecast calculation (SROI with year 1 info, forecasting for year 2)

- Summer 2026: Yearly SROI evaluative calculation (SROI assessing year 1)

- Summer 2026: Quantitative Data Analysis

- Summer 2026: School Comparison Analysis

- Summer 2026: analysis of data & writing of year 1 report

- Fall 2026: Year 1 report due

Phase 2 - Year 2-3: the following data collection activities will be expanded to any new schools participating in the program.

Year 2:

- August 2026 - May 2027: Enrollment surveys distributed

- Throughout year 2: Quarterly Arkansas Brighter Futures 529 reports sent to evaluators

- Fall 2026: Distribute Student Literacy Financial Pre Quiz

- Spring 2027: Distribute Student Literacy Financial Post Quiz

- Spring 2027: Interview with G.R.O.W ambassador

- Spring 2027: Interview with program partners

- Spring 2027: Focus group with parents of enrolled scholars

- Spring 2027: Focus group with G.R.O.W educators

- Spring 2027: Tempus cost data due to evaluators

- Summer 2027: Yearly SROI Forecast calculation (SROI with year 2 info, forecasting for year 3)

- Summer 2027: Yearly SROI evaluative calculation (SROI assessing year 2)

- Summer 2027: Quantitative Data Analysis

- Summer 2027: School Comparison Analysis

- Summer 2027: analysis of data & writing of year 1 report

- Fall 2027: Year 2 report due

Year 3:

- August 2027 - May 2028: Enrollment surveys distributed

- Throughout year 3: Quarterly Arkansas Brighter Futures 529 reports sent to evaluators

- Fall 2027: Distribute Student Literacy Financial Pre Quiz

- Spring 2028: Distribute Student Literacy Financial Post Quiz

- Spring 2028: Interview with G.R.O.W ambassador

- Spring 2028: Interview with program partners

- Spring 2028: Focus group with parents of enrolled scholars

- Spring 2028: Focus group with G.R.O.W educators

- Spring 2028: Tempus cost data due to evaluators

- Summer 2028: Yearly SROI Forecast calculation (SROI with year 3 info, forecasting for year 4)

- Summer 2028: Yearly SROI evaluative calculation (SROI assessing year 3)

- Summer 2028: Quantitative Data Analysis

- Summer 2028: School Comparison Analysis

- Summer 2028: analysis of data & writing of year 1 report

- Fall 2028: Year 3 report due

Phase 3 - Year 10-15 TBD

This evaluation plan does not address the long term research questions of Phase 3. An additional agreement would be required in the future, when the appropriate data is available, in order to address these questions.

Deliverables:

- Three annual reports: annual reports will be created by the evaluators on a yearly basis. They will include a report of program progress, as well as recommendations for program improvements moving forward.

- An updated Evaluative and Forecasted SROI per year:

  - Evaluative SROI: Each year, an evaluative SROI will be conducted for the past year of program implementation. The evaluative SROI will take into account the data from the previous year, giving the most accurate prediction of the Social impact from that program the previous year. For years 2 and 3, this can also be compared to the forecasted SROI made at the beginning of the program year.

  - Forecasted SROI: At the end of each year, a forecasted SROI will be calculated for the next year, reflecting the anticipated social impact moving forward. Calculating at the end of each year with the most recent data will provide a more accurate projection of Social Return on Investment (SROI).

- Final Slide Deck: At the end of year 3, a final slide deck will be compiled with the evaluation findings for all three years. The slidedeck will them be given to Tempus for use with stakeholders

Incentive Plan: The following table outlines the anticipated incentives for data collection participants. Totals represent the maximum number of incentives purchased and distributed. Incentive purchases will be added to the above cost as they are purchased, therefore Tempus will not be charged for incentives until they are used.

| Activity | # of Participants | Incentive Per Participant | Year 1 Total 1 school | Year 2 Total 2 schools | Year 3 Total 3 schools |
| --- | --- | --- | --- | --- | --- |
| Interview with Ambassador | 1 (per school) | $40 Walmart Gift Card | $40 | $80 | $120 |
| Focus groups with participants (i.e. parents/caregivers) | 30 (max) 3 focus groups, with max of 10 participants each | $40 Walmart Gift Card | $1200 | $1200 | $1200 |
| Focus group with G.R.O.W educators | 10 (max) 1 focus group per school | $40 Walmart Gift Card | $400 | $800 | $1200 |
| Annual follow up survey (parents & teachers) | 400 | $10 Walmart Gift Card | $4,000 | $4,000 | $4,000 |
| Annual Total |  |  | $5,640 | $6,080 | $6,520 |
| Total |  |  | $18,240 |  |  |